## TAB (1)
TA WOODS COMPANY
TWO WEEK LOOK AHEAD PLAN
Supt.
| Job Name | [6 empty] | Week 1 Ending
| Job Number | [6 empty] | Week 2 Ending
Mechanical, Electrical, Plumbing, General Construction
|  | WEEK 1 | [6 empty] | WEEK 2
What Tasks Do You Have Planned? | Identfier | Mon | Tue | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | Fri | Sat | Sun
Total Head Count |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Do we have the required material, tools and Rentals on site to perform this work?
Are Material Required to Support this Plan: | Are Equipment Rental Needed to Support this Plan? | WEEK 1 Fri: Are Specialty Tools required to Support this Plan?
What Unresolved Issues Are Critical At This Time?
NOTE: If additional space is required, please use an additional sheet.
Identifier Example: ZONE / AREA / DRWG / EMPLY INITIAL
REV DATE: 07.09.2020
3

## Narrative
2 Week Look Ahead
Directions for Completing this Form
The New Look Ahead Sheet has protected cells that cannot be changed.
Only the areas that require weekly input are unprotected.
1 | Fill in your name in the Supt. Box
2 | Fill in your job name
3 | Fill in your job number
4 | Fill in Week 1 ending date-- all weeks end of Sunday.
This date is Sunday of the following week
5 | Fill in Week 2 ending date,
There is no longer a Sheet Designation
6 | Complete the list of tasks you have planned on the lines provided.
Should you have more tasks then available on single sheet, prepare a second sheet.
7 | The column next to Task is now called "Identifier"
Use whatever Identifier you and your PM are comfortable with
Example of Identifiers: AREA, ZONE, FLOOR, BLUEPRINT, EMPLY Initials Assigned to Task
8 | List the number of men assigned Daily to each Task for the 2 week period--
This is a head count and not projected hours to complete the tasks
The lower Box Groups are to list any Material, Rentals, Tools that ARE NOT currently on site
but needed to complete the Tasks.
9 | Advise of any material needed that is NOT currently on site
10 | List any rental equipment needed that is NOT currently on site
11 | List any special tools that need to be signed out that are NOT currently on site
12 | Advise of any critical issues that need to be addressed for this 2 week look ahead--
This could be work needed completed by other trades or information needed from
the GC or the office
13 | If you need additional space to list all tasks being scheduled for the next 2 weeks,
use additional sheets. You no longer need to complete one sheet per area of work,
you can list multiple areas on the same sheet
REV | 03.01.2020