## SUMMARY (8)
UNCW P3 Student Housing | [8 empty] | Week Ending |  |  | 2020-12-13
BUILDING # 1
Job # 20.005M
Description |  | Estimate Summary |  |  |  | Current Work |  |  |  | Previous |  |  | Production Summary
| Cost | Units | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod. | Remaining
| Code | Est. | Est. | Unit | Per | this | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date | Hours
[5 empty] | Hour | Week |  |  |  |  | spent | earned |  | left |  | date | Earned | date |  | Per
[5 empty] | Per Man | [14 empty] | Job
ILM Airport | 19.027 | 3196 | 506 | 0.15832 |  | 116 | 54 | 27.2941 | 50.54% | 1010 | 436 | 212.4249 | 4268 | 266.281 | 1126 | 490 | 560 | 239.719 | 48.92% | 16
Brunswick County Courthouse | 20.004 | 2868 | 384 | 0.13389 |  | 156 | 29 | 17.5175 | 60.41% | 927 | 362 | 144.8312 | 1785 | 221.6513 | 1083 | 391 | 1042.1739 | 162.3487 | 41.52% | -7
P3 Housing | 20.005 | 5682 | 588 | 0.10348 |  | 0 | 0 | 0 | #DIV/0! | 5005 | 1114.5 | 531.2469 | 677 | 56.7531 | 5005 | 1114.5 | 560 | 531.2469 | 47.67% | -526.5
North Brunswick | 20.01 | 1483 | 158 | 0.10654 |  | 0 | 0 | 0 | #DIV/0! | 281 | 55.5 | 37.7636 | 1202 | 120.2364 | 281 | 55.5 | 638 | 37.7636 | 68.04% | 102.5
West Brunswick | 20.011 | 1952 | 246 | 0.12602 |  | 0 | 0 | 0 | #DIV/0! | 93 | 31 | 9.3 | 1859 | 236.7 | 93 | 31 | 784.2 | 9.3 | 30% | 215
Wilmington Eye Associates | 20.012 | 2529 | 302 | 0.11941 |  | 22 | 9 | 3.5044 | 38.94% | 1022 | 226.5 | 124.3609 | 1485 | 174.1347 | 1044 | 235.5 | 620 | 127.8653 | 54.3% | 66.5
TOTAL PROJECT |  | 17710 | 2184 |  |  | 294 | 92 | 48.316 | 52.52% | 8338 | 2225.5 | 1059.9274 | 11276 | 1075.7566 | 8632 | 2317.5 | 4204.3739 | 1108.2434 | 47.82%
Man-hours Posted to project this week | [6 empty] | 0 | [8 empty] | -133.5 |  | HOURS REMAINING |  | -133.5
-92
Note on O6: Brian Cox: All formulas. No Key Punch Input

## Wilm Eye (8)
Wilmington Eye Associates | [12 empty] | 2020-12-13
Job # 20.012M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
AREA A - DWG M1.1
Low Pressure Galvanized Duct | 1705 | 520 | LF | 74 | 0.14231 | 7.027 |  |  | 0 | #DIV/0! | 520 | 154.5 | 74 | 0 | 0 | 520 | 154.5 | 74 | 74 | 47.9%
Round Spiral Pipe | 1706 | 260 | LF | 20 | 0.076923 | 13 |  |  | 0 | #DIV/0! | 260 | 5 | 20 | 0 | 0 | 260 | 5 | 20 | 20 | 400%
AREA B - DWG M1.2
Low Pressure Galvanized Duct | 1705 | 180 | LF | 28 | 0.15556 | 6.4286 |  |  | 0 | #DIV/0! | 16 | 22 | 2.4889 | 164 | 25.5111 | 16 | 22 | 2.4889 | 2.4889 | 11.31%
Round Spiral Pipe | 1706 | 220 | LF | 8 | 0.036364 | 27.5 |  |  | 0 | #DIV/0! | 50 | 2 | 1.8182 | 170 | 6.1818 | 50 | 2 | 1.8182 | 1.8182 | 90.91%
AREA C - DWG M1.3
Low Pressure Galvanized Duct | 1705 | 492 | LF | 68 | 0.13821 | 7.2353 |  |  | 0 | #DIV/0! | 94 | 23 | 12.9919 | 398 | 55.0081 | 94 | 23 | 12.9919 | 12.9919 | 56.49%
Round Spiral Pipe | 1706 | 152 | LF | 6 | 0.039474 | 25.3333 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 152 | 6 | 0 | 0 | 0 | 0 | #DIV/0!
AREA D - DWG M1.4
Low Pressure Galvanized Duct | 1705 | 565 | LF | 90 | 0.15929 | 6.2778 | 22 | 9 | 3.5044 | 38.94% | 82 | 20 | 13.0619 | 461 | 73.4336 | 104 | 29 | 16.5664 | 16.5664 | 57.13%
Round Spiral Pipe | 1706 | 140 | LF | 8 | 0.057143 | 17.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 140 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 2529 |  | 302 | 0.11941 |  | 22 | 9 | 3.5044 | 38.94% | 1022 | 226.5 | 124.3609 | 1485 | 174.1347 | 1044 | 235.5 | 127.8653 | 127.8653 | 54.3%
Sub Total from Time Sheet | [7 empty] | -83
Sub Total Remaining | [7 empty] | -92
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O5: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"

## WBHS (8)
West Brunswick High School | [12 empty] | 2020-12-13
Job # 20.011M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
Cafeteria - Ductwork
Low Pressure - Galvanized Duct | 1705 | 189 | LF | 36 | 0.19048 | 5.25 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 189 | 36 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Pipe | 1706 | 38 | LF | 4 | 0.10526 | 9.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 38 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
ROTC - Ductwork
Low Pressure - Galvanized Duct | 1705 | 100 | LF | 10 | 0.1 | 10 |  |  | 0 | #DIV/0! | 93 | 31 | 9.3 | 7 | 0.7 | 93 | 31 | 9.3 | 9.3 | 30%
Round Spiral Pipe | 1708 | 22 | LF | 2 | 0.090909 | 11 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 22 | 2 | 0 | 0 | 0 | 0 | #DIV/0!
2-Story Add - LP Ductwork
Low Pressure - Galvanized Duct | 1705 | 620 | LF | 100 | 0.16129 | 6.2 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 620 | 100 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Pipe | 1706 | 200 | LF | 8 | 0.04 | 25 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 200 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
2 Story -Medium Pressure Ductwork
Medium Pressure - Galvanized Duct | 1705 | 187 | LF | 26 | 0.13904 | 7.1923 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 187 | 26 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Pipe | 1706 | 180 | LF | 6 | 0.033333 | 30 |  |  | 0 | #DIV/0! |  |  |  | 180 | 6 |  |  |  |  | #DIV/0!
Class 222 - Ductwork
Low Pressure - Galvanized Duct | 1705 | 308 | LF | 42 | 0.13636 | 7.3333 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 308 | 42 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Pipe | 1706 | 100 | LF | 8 | 0.08 | 12.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 100 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
Class 403 - Ductwork
Low Pressure - Galvanized Duct | 1705 | 8 | LF | 4 | 0.5 | 2 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 8 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 1952 |  | 246 | 0.12602 |  | 0 | 0 | 0 | #DIV/0! | 93 | 31 | 9.3 | 1859 | 236.7 | 93 | 31 | 9.3 | 9.3 | 30%
Sub Total from Time Sheet | [7 empty] | -83
Sub Total Remaining | [7 empty] | -83
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O5: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"

## NBHS (8)
North Brunswick High School | [9 empty] | Week Ending |  |  | 2020-12-13
Job # 20.010M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
Cafeteria - Ductwork
Low Pressure - Galvanized Duct | 1705 | 204 | LF | 32 | 0.15686 | 6.375 |  |  | 0 | #DIV/0! | 180 | 44 | 28.2353 | 24 | 3.7647 | 180 | 44 | 28.2353 | 28.2353 | 64.17%
Round Spiral Pipe | 1706 | 38 | LF | 4 | 0.10526 | 9.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 38 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
ROTC - Ductwork
Low Pressure - Galvanized Duct | 1705 | 106 | LF | 10 | 0.09434 | 10.6 |  |  | 0 | #DIV/0! | 101 | 11.5 | 9.5283 | 5 | 0.4717 | 101 | 11.5 | 9.5283 | 9.5283 | 82.85%
Round Spiral Pipe | 1706 | 12 | LF | 2 | 0.16667 | 6 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 12 | 2 | 0 | 0 | 0 | 0 | #DIV/0!
2-Story Add - LP Ductwork
Low Pressure - Galvanized Duct | 1705 | 436 | LF | 72 | 0.16514 | 6.0556 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 436 | 72 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Pipe | 1706 | 500 | LF | 18 | 0.036 | 27.7778 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 500 | 18 | 0 | 0 | 0 | 0 | #DIV/0!
2-Story Add - Medium Pressure Ductwork
Medium Pressure - Galvanized Duct | 1705 | 105 | LF | 16 | 0.15238 | 6.5625 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 105 | 16 | 0 | 0 | 0 | 0 | #DIV/0!
2-Story Round Ductwork - Medium Pressure
Medium Pressure - Round Duct | 1705 | 82 | LF | 4 | 0.04878 | 20.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 82 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 1483 |  | 158 | 0.10654 |  | 0 | 0 | 0 | #DIV/0! | 281 | 55.5 | 37.7636 | 1202 | 120.2364 | 281 | 55.5 | 37.7636 | 37.7636 | 68.04%
Sub Total from Time Sheet | [7 empty] | -83
Sub Total Remaining | [7 empty] | -83
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O5: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"

## P3 Housing (8)
UNCW P3 Student Housing | [12 empty] | 2020-12-13
BUILDING # 1
Job # 20.005M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
FIRST FLOOR
LP Rectangular Ductwork | 1705 | 670 | LF | 88 | 0.13134 | 7.6136 |  |  | 0 | #DIV/0! | 670 | 168 | 88 | 0 | 0 | 670 | 168 | 88 | 88 | 52.38%
Round Spiral Pipe | 1706 | 220 | LF | 8 | 0.036364 | 27.5 |  |  | 0 | #DIV/0! | 220 | 6 | 8 | 0 | 0 | 220 | 6 | 8 | 8 | 133.3%
SECOND FLOOR
LP Rectangular Ductwork | 1705 | 744 | LF | 70 | 0.094086 | 10.6286 |  |  | 0 | #DIV/0! | 744 | 196 | 70 | 0 | 0 | 744 | 196 | 70 | 70 | 35.71%
Round Spiral Pipe | 1706 | 238 | LF | 12 | 0.05042 | 19.8333 |  |  | 0 | #DIV/0! | 238 | 12 | 12 | 0 | 0 | 238 | 12 | 12 | 12 | 100%
THIRD FLOOR
LP Rectangular Ductwork | 1705 | 740 | LF | 70 | 0.094595 | 10.5714 |  |  | 0 | #DIV/0! | 740 | 196 | 70 | 0 | 0 | 740 | 196 | 70 | 70 | 35.71%
Round Spiral Pipe | 1706 | 238 | LF | 12 | 0.05042 | 19.8333 |  |  | 0 | #DIV/0! | 238 | 12 | 12 | 0 | 0 | 238 | 12 | 12 | 12 | 100%
FOURTH FLOOR
LP Rectangular Ductwork | 1705 | 740 | LF | 70 | 0.094595 | 10.5714 |  |  | 0 | #DIV/0! | 740 | 188 | 70 | 0 | 0 | 740 | 188 | 70 | 70 | 37.23%
Round Spiral Pipe | 1706 | 238 | LF | 12 | 0.05042 | 19.8333 |  |  | 0 | #DIV/0! | 238 | 12 | 12 | 0 | 0 | 238 | 12 | 12 | 12 | 100%
FIFTH FLOOR
LP Rectangular Ductwork | 1705 | 740 | LF | 70 | 0.094595 | 10.5714 |  |  | 0 | #DIV/0! | 345 | 90 | 32.6351 | 395 | 37.3649 | 345 | 90 | 32.6351 | 32.6351 | 36.26%
Round Spiral Pipe | 1706 | 238 | LF | 12 | 0.05042 | 19.8333 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 238 | 12 | 0 | 0 | 0 | 0 | #DIV/0!
ATTIC
LP Rectangular Ductwork | 1705 | 850 | LF | 160 | 0.18824 | 5.3125 |  |  | 0 | #DIV/0! | 832 | 234.5 | 156.6118 | 18 | 3.3882 | 832 | 234.5 | 156.6118 | 156.6118 | 66.79%
Round Spiral Pipe | 1706 | 26 | LF | 4 | 0.15385 | 6.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 26 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 5682 |  | 588 | 0.10348 |  | 0 | 0 | 0 | #DIV/0! | 5005 | 1114.5 | 531.2469 | 677 | 56.7531 | 5005 | 1114.5 | 531.2469 | 531.2469 | 47.67%
Sub Total from Time Sheet | [7 empty] | -83
Sub Total Remaining | [7 empty] | -83
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O6: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"

## BCCH (8)
Brunswick County Courthouse | [12 empty] | 2020-12-13
Job # 20.004M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
1st Floor - Phase 1
Rectangular Ducts - MP & LP | 1707 | 659 | LF | 74 | 0.11229 | 8.9054 | 156 | 29 | 17.5175 | 60.41% | 292 | 97 | 32.7891 | 211 | 23.6935 | 448 | 126 | 50.3065 | 50.3065 | 39.93%
Round Spiral Duct | 1706 | 4 | LF | 4 | 1 | 1 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
1st Floor - Phase 2
Rectangular Ducts - MP & LP | 1707 | 92 | LF | 18 | 0.19565 | 5.1111 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 92 | 18 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 100 | LF | 4 | 0.04 | 25 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 100 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
1st Floor - Phase 3
Rectangular Ducts - MP & LP | 1705 | 80 | LF | 14 | 0.175 | 5.7143 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 80 | 14 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 130 | LF | 6 | 0.046154 | 21.6667 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 130 | 6 | 0 | 0 | 0 | 0 | #DIV/0!
2nd Floor - Phase 1
Rectangular Ducts - MP & LP | 1705 | 404 | LF | 60 | 0.14851 | 6.7333 |  |  | 0 | #DIV/0! | 208 | 56 | 30.8911 | 196 | 29.1089 | 208 | 56 | 30.8911 | 30.8911 | 55.16%
Round Spiral Duct | 1706 | 250 | LF | 8 | 0.032 | 31.25 |  |  | 0 | #DIV/0! | 60 | 2 | 1.92 | 190 | 6.08 | 60 | 2 | 1.92 | 1.92 | 96%
2nd Floor - Phase 2
Rectangular Ducts - MP & LP | 1705 | 220 | LF | 24 | 0.10909 | 9.1667 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 220 | 24 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 130 | LF | 6 | 0.046154 | 21.6667 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 130 | 6 | 0 | 0 | 0 | 0 | #DIV/0!
2nd Floor - Phase 3
Rectangular Ducts - MP & LP | 1705 | 55 | LF | 14 | 0.25455 | 3.9286 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 55 | 14 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 20 | LF | 2 | 0.1 | 10 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 20 | 2 | 0 | 0 | 0 | 0 | #DIV/0!
3rd Floor - Phase 1
Rectangular Ducts - MP & LP | 1705 | 405 | LF | 100 | 0.24691 | 4.05 |  |  | 0 | #DIV/0! | 307 | 201.5 | 75.8025 | 98 | 24.1975 | 307 | 201.5 | 75.8025 | 75.8025 | 37.62%
Round Spiral Duct | 1706 | 70 | LF | 4 | 0.057143 | 17.5 |  |  | 0 | #DIV/0! | 60 | 5.5 | 3.4286 | 10 | 0.57143 | 60 | 5.5 | 3.4286 | 3.4286 | 62.34%
3rd Floor - Phase 2
Rectangular Ducts - MP & LP | 1705 | 70 | LF | 6 | 0.085714 | 11.6667 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 70 | 6 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 10 | LF | 2 | 0.2 | 5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 10 | 2 | 0 | 0 | 0 | 0 | #DIV/0!
M2.3 Mech Room 1203 & 2205
Rectangular Ducts - MP & LP | 1705 | 169 | LF | 38 | 0.22485 | 4.4474 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 169 | 38 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 2868 |  | 384 | 0.13389 |  | 156 | 29 | 17.5175 | 60.41% | 927 | 362 | 144.8312 | 1785 | 221.6513 | 1083 | 391 | 83.1176 | 162.3487 | 41.52%
Sub Total from Time Sheet | [7 empty] | -54
Sub Total Remaining | [7 empty] | -83
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O5: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"

## ILM (8)
ILM Airport | [12 empty] | 2020-12-13
Phase III
Job # 19.027M
|  | Estimate Summary |  |  |  |  | Current To Date |  |  |  | Previous |  |  | Production Summary
| Cost | Units |  | Hrs. | Hrs. per | Unit | Units | Hrs. | Hrs. | Prod. | Prev. | Prev. | Prev. | Units | Earnable | Units | Hrs. | Possible | Hrs. | Prod.
| Code | Est. |  | Est. | Unit | Per | TO | Spent | Earned | % | Units | Hrs. | Hrs. | left | hrs. | to date | spent to | Hrs. | Earned to | To Date
[6 empty] | Hour | DATE |  |  |  |  | spent | earned |  | left |  | date | Earned | date
Per Man
M1-121 Boarding Level (Zone 1)
Rectangular Duct | 1705 | 251 | LF | 40 | 0.15936 | 6.275 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 251 | 40 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 100 | LF | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
M1-112 Ramp Level (Zone 2)
Rectangular Duct | 1705 | 850 | LF | 200 | 0.23529 | 4.25 | 116 | 54 | 27.2941 | 50.54% | 694 | 366 | 163.2941 | 40 | 9.4118 | 810 | 420 | 190.5882 | 190.5882 | 45.38%
Round Spiral Duct | 1706 | 240 | LF | 0 | 0 | #DIV/0! |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
M1-122 Boarding Level (Zone 2)
Rectangular Duct | 1705 | 1415 | LF | 220 | 0.15548 | 6.4318 |  |  | 0 | #DIV/0! | 316 | 70 | 49.1307 | 1099 | 170.8693 | 316 | 70 | 49.1307 | 49.1307 | 70.19%
Round Spiral Duct | 1706 | 210 | LF | 26 | 0.12381 | 8.0769 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 210 | 26 | 0 | 0 | 0 | 0 | #DIV/0!
M1-113 Ramp Level (Zone 3)
Rectangular Duct | 1705 | 57 | LF | 8 | 0.14035 | 7.125 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 57 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 0 | LF | 0
M1-123 Ticket Level (Zone 3)
Rectangular Duct | 1705 | 43 | LF | 8 | 0.18605 | 5.375 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 43 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 30 | LF | 4 | 0.13333 | 7.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 30 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
M2-111 Ramp Level (Zone 1)
Rectangular Duct | 1705 | 516 | LF | 108 | 0.2093 | 4.7778 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 516 | 108 | 0 | 0 | 0 | 0 | #DIV/0!
M2-121 Boarding Level (Zone 1)
Rectangular Duct | 1705 | 546 | LF | 96 | 0.17582 | 5.6875 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 546 | 96 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 54 | LF | 4 | 0.074074 | 13.5 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 54 | 4 | 0 | 0 | 0 | 0 | #DIV/0!
M2-113 Ramp Level (Zone 3)
Rectangular Duct | 1705 | 329 | LF | 44 | 0.13374 | 7.4773 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 329 | 44 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 80 | LF | 8 | 0.1 | 10 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
M2-123 Ticket Level (Zone 3)
Rectangular Duct | 1705 | 235 | LF | 34 | 0.14468 | 6.9118 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 235 | 34 | 0 | 0 | 0 | 0 | #DIV/0!
Round Spiral Duct | 1706 | 80 | LF | 8 | 0.1 | 10 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 80 | 8 | 0 | 0 | 0 | 0 | #DIV/0!
M2-125 Ticket Level (Zone 5)
Rectangular Duct | 1705 | 358 | LF | 52 | 0.14525 | 6.8846 |  |  | 0 | #DIV/0! | 0 | 0 | 0 | 358 | 52 | 0 | 0 | 0 | 0 | #DIV/0!
TOTAL SHEET |  | 3196 |  | 506 | 0.15832 |  | 116 | 54 | 27.2941 | 50.54% | 1010 | 436 | 212.4249 | 4268 | 266.281 | 1126 | 490 | 239.719 | 239.719 | 48.92%
Sub Total from Time Sheet | [7 empty] | 0 | <------ ENTER TOTAL WORK WEEK HOURS HERE FOR SHOP
Sub Total Remaining | [7 empty] | -54
788
BEQ A |  | 1090 |  | 2970 |  | 2.72 |  | 2429 | 541 | 198.8971
BEQ B |  | 1090 |  | 2970 |  | 2.72 |  | 482 | 2488 | 914.7059
BEQ C |  | 1090 |  | 2970 |  | 2.72 |  | 192 | 2778 | 1021.3235
0
[7 empty] | 27 | 5 | 135 | 5 | 675
0
0
Note on O5: Brian Cox: All formulas. No Key Punch Input
Note on T50: BCox: copy this column to column N. Cannot swipe all three because of hidden column "S"